## Review Approval Log
Document Review & Approval Log - Jeddah Tower DCMS
Document ID | Document Title | Revision | Review Cycle | Originator | Technical Reviewer | Discipline Lead | Project Manager | Review Start | Review Due | Current Status | Approval Status | Comments | Next Action
JTDCMS-CIV-DRW-001-A | General Arrangement Drawing | A | 1 | Civil Engineer | Reviewed | Pending | Pending | 2026-07-05 | 2026-07-12 | Under Review | Pending | Minor comments raised | Originator to revise
JTDCMS-QA-ITP-001-A | Inspection & Test Plan | A | 1 | QA/QC Engineer | Approved | Approved | Approved | 2026-07-03 | 2026-07-08 | Completed | Approved | No comments | Issue for use
JTDCMS-CIV-MTS-001-A | Concrete Method Statement | A | 1 | Site Engineer | Reviewed | Reviewed | Pending | 2026-07-04 | 2026-07-11 | Awaiting PM | Pending | Major comments resolved | PM approval
JTDCMS-DC-PRO-001-0 | Document Control Procedure | 0 | 1 | Document Controller | Approved | Approved | Approved | 2026-07-01 | 2026-07-05 | Closed | Approved | Initial release | Archive review record