## Master Document Register
Master Document Register (MDR) - Jeddah Tower DCMS
Doc ID | Document Title | Discipline | Document Type | Revision | Status | Originator | Reviewer | Approver | Current Holder | Latest Transmittal | Issue Date | Next Review | EDMS Location | Remarks
JTDCMS-QA-POL-001-A | Quality Policy | QA | Policy | A | Approved | Quality Manager | Quality Manager | Project Director | All Staff | TRN-001 | 2026-07-01 | 2027-07-01 | /QMS/Policies
JTDCMS-DC-PRO-001-0 | Document Control Procedure | DC | Procedure | 0 | Approved | Document Controller | Quality Manager | Project Director | Project Team | TRN-002 | 2026-07-01 | 2027-07-01 | /QMS/Procedures
JTDCMS-CIV-DRW-001-A | General Arrangement Drawing | CIV | Drawing | A | Under Review | Civil Engineer | Civil Lead |  | Engineering | - |  |  | /Engineering/Drawings | Pending approval
JTDCMS-QA-ITP-001-A | Inspection & Test Plan | QA | ITP | A | Approved | QA/QC Engineer | QA Manager | Project Manager | QA/QC Team | TRN-003 | 2026-07-02 | 2026-10-02 | /QAQC/ITP
JTDCMS-PM-MOM-001-A | Kick-off Meeting Minutes | PM | Minutes | A | Approved | Project Coordinator | Project Manager | Project Manager | Project Team | TRN-004 | 2026-07-01 | - | /PM/Meetings
JTDCMS-DC-TRN-001-A | Client Incoming Transmittal | DC | Transmittal | A | Received | Document Controller | Document Controller | N/A | Document Control | - | 2026-07-01 | - | /DC/Transmittals