## Revision Register
Document Revision Register - Jeddah Tower DCMS
Document ID | Document Title | Revision | Previous Revision | Revision Date | Change Request | Change Summary | Originator | Reviewed By | Approved By | Status | Remarks
JTDCMS-QA-POL-001-A | Quality Policy | A | - | 2026-07-01 | N/A | Initial approved issue | Quality Manager | Quality Manager | Project Director | Approved
JTDCMS-DC-PRO-001-0 | Document Control Procedure | 0 | - | 2026-07-01 | N/A | Initial procedure release | Document Controller | Quality Manager | Project Director | Approved
JTDCMS-CIV-DRW-001-B | General Arrangement Drawing | B | A |  | DCR-001 | Updated foundation layout | Civil Engineer | Civil Lead |  | Under Review | Pending approval
JTDCMS-QA-ITP-001-B | Inspection & Test Plan | B | A |  | DCR-002 | Inspection hold points updated | QA/QC Engineer | QA Manager |  | Draft | Awaiting review
JTDCMS-PM-MOM-001-A | Kick-off Meeting Minutes | A | - | 2026-07-01 | N/A | Original issue | Project Coordinator | Project Manager | Project Manager | Approved