## KPI Dashboard
Document Control KPI Dashboard - Jeddah Tower DCMS
KPI | Target | Jan | Feb | Mar | Apr | May | Jun | Current | Status | Trend | Action Required
Overdue Document Reviews | 0 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | On Target | Improving | Continue monitoring
Average Review Turnaround (days) | ≤7 | 8 | 7 | 7 | 6 | 6 | 5 | 5 | On Target | Improving | Maintain performance
Document Retrieval Time (min) | <2 | 2.5 | 2.2 | 2.0 | 1.9 | 1.8 | 1.6 | 1.6 | On Target | Improving | Maintain EDMS indexing
Transmittal Acknowledgment Rate | ≥95% | 90% | 92% | 94% | 95% | 97% | 98% | 98% | On Target | Improving | Maintain follow-up
EDMS Upload Success Rate | 100% | 97% | 98% | 99% | 100% | 100% | 100% | 100% | On Target | Stable | Routine validation
Open NCRs | 0 | 4 | 3 | 2 | 2 | 1 | 0 | 0 | Closed | Improving | Continue CAPA verification
CAPA Closure Within 14 Days | 100% | 80% | 85% | 90% | 95% | 100% | 100% | 100% | On Target | Improving | Monitor deadlines
Backup Success Rate | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On Target | Stable | Routine testing