## NCR & CAPA Register
NCR & CAPA Register - Jeddah Tower DCMS
NCR No. | Date Raised | Audit Ref. | Department | Nonconformity | Root Cause (5 Whys) | Risk Level | Corrective Action | Preventive Action | Responsible Person | Target Date | Status | Verification Date | Verified By | Remarks
NCR-001 | 2026-07-20 | AUD-001 | Document Control | Master Document Register not updated | Weekly update missed | Medium | Update register and verify records | Implement weekly review schedule | Document Controller | 2026-07-27 | Closed | 2026-07-28 | Quality Manager
NCR-002 | 2026-07-21 | AUD-001 | Engineering | Superseded drawing found on site | Recall process not followed | High | Recall obsolete drawing immediately | Monthly field verification | Site Engineer | 2026-07-24 | Closed | 2026-07-25 | Quality Manager
NCR-003 | 2026-07-22 | AUD-001 | EDMS | User had incorrect permissions | Permission review not completed | High | Correct user permissions | Quarterly access review | IT Administrator | 2026-07-29 | Open |  |  | Awaiting verification
NCR-004 | 2026-07-23 | AUD-001 | QA/QC | Transmittal acknowledgments below KPI | Late recipient responses | Medium | Follow up outstanding acknowledgments | Automated reminder process | Document Controller | 2026-07-30 | In Progress
NCR-005 | 2026-07-24 | AUD-001 | IT | Backup recovery test overdue | Recovery schedule not monitored | Medium | Complete recovery test | Monthly recovery calendar | IT Administrator | 2026-07-31 | Open