## Controlled Document Register
Controlled Document Register - Jeddah Tower DCMS
Document ID | Document Title | Category | Discipline | Revision | Status | Owner | Reviewer | Approver | Issue Date | Storage Location | Retention | Remarks
JT-DCMS-QA-POL-001 | Quality Policy | Quality | QMS | A | Approved | Quality Manager | Quality Manager | Project Director | 2026-07-01 | EDMS/QMS | Project + 10 Years
JT-DCMS-QA-PRO-001 | Document Control Procedure | Procedure | QMS | 0 | Approved | Document Controller | Quality Manager | Project Director | 2026-07-01 | EDMS/Procedures | Project + 10 Years
JT-DCMS-ENG-DRW-001 | General Arrangement Drawing | Engineering | Civil | A | Under Review | Civil Engineer | Discipline Lead | Project Manager | N/A | EDMS/Drawings | Project + 10 Years
JT-DCMS-QA-MTH-001 | Concrete Work Method Statement | Method Statement | Civil | A | Draft | Site Engineer | QA/QC Manager | Project Manager | N/A | EDMS/Method Statements | Project + 10 Years
JT-DCMS-QA-ITP-001 | Inspection & Test Plan | QA/QC | Civil | A | Approved | QA/QC Engineer | QA/QC Manager | Project Manager | 2026-07-02 | EDMS/QAQC | Project + 10 Years
JT-DCMS-PROC-MTS-001 | Material Submittal - Reinforcement Steel | Commercial | Procurement | A | Submitted | Procurement Engineer | QA/QC Manager | Consultant | N/A | EDMS/Submittals | Project + 10 Years
JT-DCMS-PMO-MOM-001 | Kick-off Meeting Minutes | Project | PMO | A | Approved | Project Coordinator | Project Manager | Project Manager | 2026-07-01 | EDMS/Meetings | Project + 10 Years
JT-DCMS-DC-TRN-001 | Incoming Client Transmittal | Transmittal | Document Control | A | Received | Document Controller | Document Controller | N/A | 2026-07-01 | EDMS/Transmittals | Project + 10 Years